STAMP PAPER

Agreement for

Construction of TW(Solar) /PDW (Solar) through Item rate contract

ARTICLES OF AGREEMENT

Agreement No.-…….…./DPMU/Paschim Medinipur /2024-25                                          Date: ……………

1.	This deed of agreement is made in the form of agreement on  ________ day _______________ month ____________ 20 ___, between the _____________________________ (Employer) or his authorized representative (hereinafter referred to as the first party) and _____________________ (Name of the Contractor),  S/O _______________ resident of ______________  (hereinafter referred to as the second party), to execute the work of construction of __________________________ (hereinafter referred to as works) on the following terms and conditions.

2.	Cost of the Contract

The total cost of the works (hereinafter referred to as the “total cost”) is Rs. ____  as reflected in Annexure - 1.

3.	Payments under the contract:

Payments to the second party for the construction work will be released by the first party in the following manner:-

For  Tube Well Solar the payment milestone will be categorized into two different milestones

- Commissioning of Tube Well and other auxiliary structures according to bill of quantities with testing report of tube well yield as per required output.

Milestone 1 :	 94% of payment should be released after commissioning of Tube Well and all construction related part with successful operation of Tube Well.

Milestone 2: 	6% Retention money will be released after One Year successful operation of Tube Well. (Defect liability Period)

- Commissioning of Solar Systems with pumps complete Installation Solar panels and Solar related support structure as per specifications mentioned in BOQ.

Milestone 1: 	 60% of payment should be released after complete Installation of Solar panels and support structure as per specifications mentioned in BOQ. The tube well pumping data should be supported by RMS and after obtaining the First/ Primary data in the main server of RMS at the office of the Client /authorized personnel.

Milestone 2:	20% of payment will be released after Acquisition of pumping information with flow and working data on RMS including solar power plant energy data, running time and yield of tube well flow for at least 120 hours of pump running

.

Milestone 3: 	6% Retention money will be released after One Year successful operation of Solar Panels with Tube Well. (Defect liability Period)

Milestone 4: 	Rest 14% would be paid in 4 (Four) installments after successful completion of operation and maintenance period at the end of every year @ 3.5 % per year after defective liability period covering warranty, insurance  and all type comprehensive AMC conditions. In case the contractor does not provide service during the warranty & comprehensive maintenance period, the amount so held up will be   forfeited.

(The above milestones can be changed as per the contract and upon the sole-discretion authority of Employer)

3.1 Deleted

3.2	The Employer shall retain (Retention Money) 6% of the amount from each payment due to the Contractor. The Performance Security shall be valid until a date of 28 days after the scheduled Completion period of works. Retention Money will be released as per Milestone.

3.3	Payments at each stage will be made by the first party:

- on the second party submitting an invoice for an equivalent amount;

(b)	on certification of the invoice (except for the first installment) by the engineer nominated by the first party with respect to quality of works in the format in Annexure - 2; and

4.	Notice by Contractor to Engineer

The second party, on the works reaching each stage of construction, shall issue a notice to the first party or the Engineer nominated by the first party [who is responsible for supervising the contractor, administering the contract, certifying payments due to the contractor, issuing and valuing variations to the contract, awarding extension of time etc.]to visit the site for certification of stage completion. Within 15 days of the receipt of such notice, the first party or the engineer nominated by it, will ensure issue of stage completion certificate after due verification.

5.	Completion time

The works should be completed in 6(months) from the date of this Agreement. In exceptional circumstances, the time period stated in this clause may be extended in writing by mutual consent of both the parties.

The “Defects Liability Period” for the work is 12 (Twelve) months from the date of taking over possession. .During this period, the contractor will be responsible for rectifying any defects in construction free of cost to the Employer.  Annual Maintenance period 5 Yrs.from   Date of Completion.

6.	If any of the compensation events mentioned below would prevent the work being completed by the intended completion date, the first party will decide on the intended completion date being extended by a suitable period:

- The first party does not give access to the site or a part thereof by the agreed period.

- The first party orders a delay or does not issue completed drawings, specifications or instructions for execution of the work on time.

- Ground conditions are substantially more adverse than could reasonably have been assumed before issue of letter of acceptance and from information provided to second party or from visual inspection of the site.

- Payments due to the second party are delayed without reason.

- Certification for stage completion of the work is delayed unreasonably.

7.	Any willful delay on the part of the second party in completing the construction within the stipulated period   will   render   him liable to   pay   liquidated damages. @ Rs. ____________ per day which will be deducted from payments due to him. The first party may cancel the contract and take recourse to such other action as deemed appropriate once the total amount of liquidated damages exceeds 5 % of the contract amount.

(@Note: The amount of liquidated damages per day should be determined at not less than 0.05 % of the contract value of the works and indicated here).

8.	Duties and responsibilities of the first party

8.1	The first party shall be responsible for providing regular and frequent supervision and guidance to the second party for carrying out the works as per specifications. This will include written guidelines and regular site visit of the authorized personnel of the first party, for checking quality of material and construction to ensure that it is as per the norms.

8.2	The first party shall supply 3 sets of drawings, specifications and guidelines to the second party for the proposed works. The Bid Document is part of agreement.

8.3	Possession of the site will be handed over to the second party within 10 days of signing of the agreement.

8.4	The Engineer or such other person as may be authorized by the first party shall hold meeting once in a month where the second party or his representative at site will submit the latest information including progress report and difficulties if any, in the execution of the work. The whole team may jointly inspect the site on a particular day to take stock of activities.

8.5	The Engineer shall record his observations/instructions at the time of his site visit in a site register maintained by the second party.  The second party will carry out the instructions and promptly rectify any deviations pointed out by the engineer.  If the deviations are not rectified, within the time specified in the Engineer’s notice, the first party as well as the engineer nominated by it, may instruct stoppage or suspension of the construction.  It shall thereupon be open to the first party or the engineer to have the deviations rectified at the cost of the second party.

8.6	The Engineer shall issue a Certificate of Completion of the Works on the request of the second party, and upon deciding that the whole of the Works is completed.

9.	Duties and responsibilities of the second party

9.1	The second party shall:

- take up the works and arrange for its completion within the time period stipulated in clause 5;

- employ suitable skilled persons to carry out the works;

- regularly supervise and monitor the progress of work;

- abide by the technical suggestions/ direction of supervisory personnel including engineers etc. regarding building construction;

- be responsible for bringing any discrepancy to the notice of the representative of the first party and seek necessary clarification;

- ensure that the work is carried out in accordance with specifications, drawings and within the total of the contract amount without any cost escalation;

- keep the first party informed about the progress of work;

- correct the notified defects within the length of time specified by the Engineer;

- be responsible for all security and watch and ward arrangements at site till handing over of the works to the first party;

- maintain necessary insurance against loss of materials/cash, etc. or workman disability compensation claims of the personnel deployed on the works as well as third party claims from the start date to the end of defect liability period;

- pay all duties, taxes and other levies payable by construction agencies as per law under the contract (First party will effect deduction from running bills in respect of such taxes as may be imposed under the law);

- abide by the regulatory authority conditions (if any) attached to any permits or approvals for the project; and the ESHS Management Strategies and Implementation Plan and ESHS Code of Conduct, if any prescribed by the Employer;

- abide by all labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authorities;

- abide by all enactments on environmental protection and rules made there under, regulations, notifications and by-laws of the Sate or Central Government, or local authorities;

- be responsible for the safety of all activities on the Site.

10.	Variations / Extra Items

The works shall be executed by the second party in accordance with the approved drawings and specifications.  No variation in cost is acceptable.  However, if the Engineer issues instructions for execution of extra items, the following procedure shall be followed:-

- The second party shall provide the Engineer with a quotation for carrying out the extra items when requested to do so by the Engineer.  The Engineer shall assess the quotation, which shall be given within seven days of the request before the extra items are ordered.

- If the quotation given by the second party is unreasonable, the Engineer may order the extra items and make a change to the Contract Price which shall be based on Engineer’s own forecast of the effects of the extra items on the Contractor’s costs.

- The second party shall not be entitled to additional payment for costs, which could have been avoided by giving early warning.

11.	Securities

The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount and form and by a bank acceptable to the Employer.  The Performance Security shall be valid until a date of 28 days after the scheduled Completion period of works, in the case of a Bank Guarantee.

12.	Termination

12.1	The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

12.2	Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	the contractor stops work for 28 days and the stoppage has not been authorized by the Engineer;

(b)	the Contractor has become bankrupt or goes into liquidation other than for a reconstruction or amalgamation;

(c)	the Engineer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Engineer;

(d)	the Contractor does not maintain a security which is required;

(e)	the Contractor has engaged in Fraud and Corruption as defined in Section C, in competing for or in executing the Contract; and

(f)	the contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid

12.3	Notwithstanding the above, the Employer may terminate the Contract for convenience.

12.4	If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

13.	Payment upon Termination

13.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of the work done less advance payments received up to the date of the issue of the certificate, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law.

13.2	If the Contract is terminated at the Employer’s convenience, the Engineer shall issue a certificate for the value of the work done, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract and less taxes due to be deducted at source as per applicable law.

14.	Dispute settlement

If over the works, any dispute arises between the two parties, relating to any aspects of this Agreement, the parties shall first attempt to settle the dispute through mutual and amicable consultation.

In the event of agreement not being reached, the matter will be referred for arbitration by a Sole Arbitrator not below the level of retired Chief Engineer / Superintending Engineer, (not connected in part or whole with this Project in his service) to be appointed by the first party. The Arbitration will be conducted in accordance with the Arbitration and Conciliation Act, 1996.  The decision of the Arbitrator shall be final and binding on both the parties.

15.	Fraud and Corruption

The World Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the WBG’s Sanctions Framework, as set forth in Section C. In further pursuance of this policy, the Contractor shall permit and shall cause its sub-contractors, sub-consultants, service providers, suppliers, agent personnel, to permit the Bank to inspect all accounts ,records, and other documents relating to the procurement process, selection and/or contract execution, and to have them audited by auditors appointed by the Bank.

********************************************************************************************************

Signature of Contractor                                                                                       Signature of Employer

In case of a firm insert ‘complete address of the firm’. In case of an individual contractor insert identification like ‘son of and resident of’ etc.